## Week 2
Business 321 - Organizational Leadership -Leadership Project Template
Due Date | Describe the service activities in enough detail that the reader can visualize the project.
Week 2 | I will lead a team of three people (including myself, my wife Brithany, and my aunt Aura) to plan, organize, and carry out a spiritual and historical service trip from Quetzaltenango (Xela) to Guatemala City to visit the Guatemala City Temple. Brithany will coordinate and book appropriate accommodations in the capital for our three-day stay (Friday through Monday). Aura will be responsible for researching, obtaining quotes for, and coordinating all safe transportation from Xela to the capital, as well as any necessary local travel. I will handle the overall financial planning, the budget for meals, per diem expenses, and the itinerary. During the trip, the team will also provide support and assistance to family members or acquaintances in the capital who wish to coordinate service activities and spiritual support, documenting the experience and assisting with hospitality tasks.
What need will your project address?
Need: The project addresses the spiritual and family well-being needs of strengthening faith and enabling family members from Xela (such as my aunt Aura) to travel safely and in an organized manner to visit the temple in Guatemala City. Why It’s Important: Visiting the temple renews spiritual strength, but making the long trip from Quetzaltenango to the capital involves logistical barriers—such as long-distance transportation, lodging, and costs—that make it difficult for people to achieve this goal on their own. How I identified it: While talking with my family in Xela, I noticed their deep desire to travel to the capital to visit the temple, but the lack of clear logistical organization and a defined budget from the western part of the country prevented them from making it happen.
Explain how you will lead, motivate, coordinate, delegate, and develop the team.
Leadership Role: Instead of doing all the work myself, I will exercise leadership through others by delegating key responsibilities based on each member’s strengths: Brithany Ramos (Wife): She will lead the accommodations section in Guatemala City. She will develop skills in negotiation, resource management, and logistical decision-making. Aura Calderon (Aunt): She will lead the coordination of intercity transportation (from Xela to the capital and back). She will develop skills in route planning, effective communication, and problem-solving. Motivation and Coordination: I will hold brief weekly follow-up meetings to align expectations, review progress, offer support, and motivate the team by reminding them of the project’s spiritual and meaningful purpose.
Write one Specific, Measurable, Achievable, Relevant, and Time-bound goal.
Coordinate a team of three people to plan, fund, and carry out a three-day trip focused on service and spiritual inspiration from Quetzaltenango to Guatemala City (traveling from Friday to Monday during Week 6), securing intercity transportation, accommodations in the capital, and the budget, and completing a total of 45 collective hours of planning, preparation, and execution by the end of Week 6.
Explain how your team will achieve the required 40 collective hours across planning, preparation, and service.
Breakdown of Team Hours (Total: 45 hours for the 3-person team): Planning (Weeks 2–3): 15 hours total (5 hours per person) researching transportation options from Xela, getting quotes for hotels in Guatemala City, creating a meal budget, and setting the travel itinerary. Preparation (Weeks 4–5): 15 hours total (5 hours per person) booking tickets/transportation, confirming accommodations in the capital, organizing per diem expenses, and preparing support logistics. Execution and Service (Week 6): A total of 15 hours (5 hours per person) carrying out the 3-day trip (Friday through Monday) from Xela to the capital, coordinating local transportation, providing logistical and on-site support at the temple, and evaluating the experience.

## Week 3
Business 321 - Organizational Leadership - Leadership Project Template (Week 3)
Due Date | Confirmed Team: List each team member and confirm participation.
All team members (Brithany Ramos, Aura Calderon, and myself) fully completed their participation as confirmed in Week 2. No team changes occurred. The trip was successfully executed on Saturday, September 12, aligning directly with our leadership objective to build distributed capability and strengthen family spiritual well-being.
Week 3
Task Breakdown and Delegation: Assign major tasks and explain each assignment.
Accommodations & Capital Logistics: Led by Brithany Ramos. Rationale: She successfully managed lodging arrangements in Guatemala City, strengthening her skills in resource management and logistical coordination. Intercity Transportation & Routes: Led by Aura Calderon. Rationale: She coordinated safe travel and routes from Quetzaltenango to the capital, expanding her communication and problem-solving abilities. Financial Planning & Team Coordination: Managed by myself. Rationale: I oversaw overall budgeting, meal per diems, and schedule tracking without centralizing operational execution.
Timeline: Week 4, Week 5, and Week 6 milestones.
Week 4 (Preparation & Execution): Finalized transportation, booked lodging, and successfully carried out the 3-day service trip from Xela to Guatemala City (completed Saturday, Sept 12). Week 5 (Documentation & Hours Tracking): Consolidate project notes, verify the 45 collective service hours, and compile family feedback. Week 6 (Final Project Verification): Conduct final post-trip evaluation and submit the verified leadership report by the end of Week 6.
Resources Needed: Materials, supplies, permissions, and acquisition plan.
We required intercity transport, lodging, meal per diems, and temple appointment passes. All resources were obtained during Week 4 via advance phone bookings, cash budgeting, and online scheduling prior to travel.
Potential Challenges: List 2–3 obstacles and backup plans.
Challenge 1 (Traffic & Route Delays): Backup Plan Implemented: Built flexible buffer time into the travel schedule to absorb traffic delays between Xela and Guatemala City without missing temple appointments. Challenge 2 (Lodging Availability): Backup Plan Implemented: Pre-selected secondary lodging options in advance to ensure accommodation security.
Coordination Contact: Name and relationship of project verifier.
External Verifier: Robin Velasquez, Bishop. Relationship: External ecclesiastical leader who verifies our project completion, team service hours, and overall spiritual impact.

## Week 4
Business 321 - Organizational Leadership - Leadership Project Template (Week 4)
Due Date | Status Update: Progress, total team hours, and comparison to Week 3 plan.
Our team successfully completed our main project objective: the 3-day spiritual service trip from Quetzaltenango to Guatemala City. All team members (Brithany, Aura, and myself) executed their delegated roles. The team has accumulated 45 total hours across planning and execution. We are fully on track with our plan as we transition into post-trip documentation and reflection.
Week 4
Leadership Challenge: Describe a leadership moment and connect it to a course principle.
During travel coordination, we encountered heavy traffic between Xela and Guatemala City. Instead of dictating a rigid change, I involved the team to adjust our itinerary buffer times collaboratively. This connects to Chapter 4’s principle of honoring agency over control, allowing team members to contribute judgment rather than relying on centralized commands.
Team Dynamics: What is working well? What needs improvement?
Our team is working exceptionally well through clear communication and shared spiritual purpose. Assigning specific operational areas (lodging to Brithany and route planning to Aura) empowered each member. What needs continuous focus is ensuring everyone feels supported when unexpected schedule changes arise.
Developing Others: Example of helping a team member grow.
I gave Brithany full ownership of booking and managing our capital accommodations. Rather than taking over the reservations, I trusted her decisions, which built her confidence in resource management and logistical execution.
Adjustments: Changes made and how the team is involved.
We implemented our contingency buffer time to absorb travel delays without disrupting temple schedules. I involved the team by holding brief check-ins to invite their input before altering travel routes or daily timelines.

## Week 5
Business 321 - Organizational Leadership - Leadership Project Template (Week 5)
Due Date | Logistics Confirmed: Date, time, location, and transportation.
Week 5
Team Readiness: Attendance confirmation, roles, and concerns.
Resources Secured: Materials obtained and remaining needs.
Execution Plan: Order of activities and leaders.
Documentation Plan: Person responsible for photos and completion confirmation.

## Week 6
Business 321 - Organizational Leadership - Leadership Project Template (Week 6)
Due Date | Completion Confirmation: Service date and total team hours.
Week 6
Team Participation: Members and responsibilities.
Outcome Summary: Results compared with SMART goal.
Leadership Moment: Challenge or decision you led.
Verification: Confirmation from service contact.
Photo Confirmation: 3–5 photos for Week 7.

## Week 7
Business 321 - Organizational Leadership - Leadership Project Template (Week 7)
Due Date | Leadership Choices: What leadership choices did you make? Which were most effective? Which would you change?
Week 7
Leading Through Others: How effectively did you delegate, coordinate, motivate, and develop your team? Provide examples.
Developing Others: What growth did you observe in your team members? How did your leadership contribute?
Course Concepts Applied: Which leadership principles from the course did you apply? How did they affect the results?
Successes and Challenges: What went well? What could have gone better? What factors contributed to each?
Future Leadership: How has this experience shaped your understanding of leadership? What will you do differently next time?
Project Documentation: Insert 3–5 photos, captions, and screenshots of social media posts (if applicable).
Final Metrics: Report total team hours, number of participants, quantifiable outcomes, and comparison to the original SMART goal.