## PROJECT DETAILS
PROJECT DEFECT TRACKER
PROJECT DETAILS
PROJECT No: | CSE270-1
DATE: | 2026-01-29
FULL PROJECT NAME: | Teton Chamber of Commerce
PROJECT MANAGER: | Saúl Abraham Arana Calderón
PROJECT SPONSOR:

## DEFECT TRACKER
DEFECT / ISSUE TRACKER
|  |  |  | User Impact | Business impact
Status | Count |  | 1-Critical | 0 | 0
1-New | 8 |  | 2-High | 0 | 0
2-Open | 0 |  | 3-Medium | 4 | 3
3-Closed | 0 |  | 4-Low | 4 | 5
TOTALS | 8 |  |  | 8 | 8
Defect ID | Detected Date | Status | H/M/L User impact | H/M/L Business impact | Subject | Reported by | Defect / issue description | Environment | Customer facing update | Internal Update | Assigned to
1 | 2026-01-29 | 1-New | 4-Low | 4-Low | Call-to-Action Button Label Incorrect | Saúl Abraham Arana Calderón | The button intended as a call-to-action on the Home page is labeled as “Join Button” instead of “Call-to-Action Button” as specified in the requirements. This may cause confusion for users expecting a call-to-action button. | Tested on Firefox on Linux 6.18.6
2 | 2026-01-29 | 1-New | 3-Medium | 4-Low | Event Dates Not Displayed | Saúl Abraham Arana Calderón | The Local Events section on the Home page displays event titles but does not display the event dates. Users cannot see when events are scheduled. | Tested on Firefox on Linux 6.18.6
3 | 2026-01-29 | 1-New | 4-Low | 4-Low | First Name Field Restriction Prevents Testing | Saúl Abraham Arana Calderón | The First Name field on the Join page does not allow entering more than 20 characters. This prevents testing the validation for maximum length as specified in the requirements. Users cannot input longer names for testing purposes. | Tested on Firefox on Linux 6.18.6
4 | 2026-01-29 | 1-New | 4-Low | 4-Low | Last Name Field Restriction Prevents Testing | Saúl Abraham Arana Calderón | The Last Name field on the Join page does not allow entering more than 20 characters. This prevents testing the validation for maximum length as specified in the requirements. Users cannot input longer names for testing purposes. | Tested on Firefox on Linux 6.18.6
5 | 2026-01-29 | 1-New | 4-Low | 4-Low | Business Name Field Restriction Prevents Testing | Saúl Abraham Arana Calderón | The Business Name field on the Join page does not allow entering more than 40 characters. This prevents testing the validation for maximum length as specified in the requirements. Users cannot input longer names for testing purposes. | Tested on Firefox on Linux 6.18.6
6 | 2026-01-29 | 1-New | 3-Medium | 3-Medium | Membership Level Not Required on Form Submission | Saúl Abraham Arana Calderón | On the Join page, the Membership Level selection is displayed but the form can be submitted without selecting any membership level. According to the requirements, form submission should be prevented and validation feedback should be shown when no membership level is selected. | Tested on Firefox on Linux 6.18.6
7 | 2026-01-29 | 1-New | 3-Medium | 3-Medium | Member Website Link Not Clickable in List View | Saúl Abraham Arana Calderón | In the Directory page List view, the member website text labeled “Website” is not clickable. Clicking the text does not open the member’s website in a new browser tab as required. | Tested on Firefox on Linux 6.18.6
8 | 2026-01-29 | 1-New | 3-Medium | 3-Medium | Member Website Link Not Clickable in Grid View | Saúl Abraham Arana Calderón | In the Directory page Grid/Card view, the member website text labeled “Website” is not clickable. Clicking the text does not open the member’s website in a new browser tab as required by the acceptance criteria. | Tested on Firefox on Linux 6.18.6
9 |  | [Blank] | [Blank] | [Blank]
10 |  | [Blank] | [Blank] | [Blank]
11 |  | [Blank] | [Blank] | [Blank]
12 |  | [Blank] | [Blank] | [Blank]
13 |  | [Blank] | [Blank] | [Blank]
14 |  | [Blank] | [Blank] | [Blank]
15 |  | [Blank] | [Blank] | [Blank]

## Dropdowns
Status
1-New
2-Open
3-Closed
[Blank]
Severity
1-Critical
2-High
3-Medium
4-Low
[Blank]